## ISO27001
Control/Requirement | Description | Evidence | Status (✅/⚠️/❌) | Gap | Recommended Action | Owner | Due Date
A.5 Information security policies | Policies approved by management and communicated | InfoSec Policy v1.2 (signed by CEO, Mar 2025) | ✅ | None | Annual review | CISO | 2025-12-31
A.6 Organization of information security | Roles, responsibilities; segregation of duties | Org chart; role descriptions | ✅ | None | Annual review | HR & IT | 2025-12-31
A.8 Asset management | Inventory of assets; ownership; classification | Asset inventory.xlsx (last updated Aug 2025) | ⚠️ | Asset classification inconsistent | Update classification labels & train staff | IT Asset Manager | 2025-09-30
A.9 Access control | User access provisioning; MFA; least privilege | IAM logs; MFA enrollment report (85% coverage) | ⚠️ | MFA not enforced org-wide | Mandate MFA for all users by policy | IT Security Lead | 2025-10-15
A.12 Operations security | Change management; logging and monitoring | Change mgmt tickets; Splunk monitoring dashboards | ✅ | None | – | Ops Manager | 2025-09-30
A.14 System acquisition, development and maintenance | Secure SDLC; testing; vulnerability management | SDLC policy; SAST/DAST scan reports | ⚠️ | Secure coding guidelines outdated | Update secure coding policy; dev training | DevSecOps Lead | 2025-10-30
A.16 Information security incident management | IR plan; roles; testing; lessons learned | IR Plan v1.0; last test Dec 2023 | ❌ | IR plan not tested in 2024 | Schedule annual tabletop exercise | IR Coordinator | 2025-11-15
A.18 Compliance | Legal and contractual requirements; privacy; audit | GDPR policy; audit log of DSARs | ⚠️ | Evidence retention incomplete | Enhance DSAR evidence tracking | DPO | 2025-11-30

## GDPR
Control/Requirement | Description | Evidence | Status (✅/⚠️/❌) | Gap | Recommended Action | Owner | Due Date
Article 30 - RoPA | Records of Processing Activities maintained | RoPA.xlsx updated Aug 2025 | ✅ | None | Review quarterly | DPO | 2025-12-31
Article 6 - Lawful Basis | Lawful basis documented for each processing activity | Lawful basis register (Consent, Contract, Legitimate Interest) | ✅ | None | Review annually | DPO | 2025-12-31
Articles 12-23 - Data Subject Rights | DSAR process within 30 days; verification; logging | DSAR log (avg 40 days response) | ⚠️ | Responses often exceed 30-day SLA | Implement SLA tracker; automate reminders | Support Manager | 2025-09-30
Article 28 - Processors | DPAs with processors; due diligence; subprocessor list | DPAs signed with 4/6 processors | ⚠️ | 2 vendors missing updated DPAs | Complete DPAs with remaining vendors | Legal Counsel | 2025-10-15
Article 32 - Security of Processing | Appropriate technical/organizational measures | AWS/Azure security whitepapers; encryption enabled | ✅ | None | Annual review | Cloud Sec Lead | 2025-09-30
Articles 33/34 - Breach Notification | 72-hour reporting to SA; data subject notification process | Incident log; breach comms template | ✅ | None | Annual breach drill | IR Coordinator | 2025-10-15
Data Retention | Defined retention schedules; deletion processes | Data retention schedule draft (not enforced) | ❌ | No deletion process implemented | Implement deletion workflows; monitor compliance | DPO | 2025-11-30
International Transfers | SCCs/adequacy decisions documented; TIAs where needed | SCCs in place; TIA missing for US vendor | ⚠️ | TIA for US processor missing | Conduct TIA; update vendor contracts | Legal Counsel | 2025-12-15

## PCI DSS
Control/Requirement | Description | Evidence | Status (✅/⚠️/❌) | Gap | Recommended Action | Owner | Due Date
Req 1 | Install and maintain network security controls (firewalls) | Firewall ruleset (reviewed Q2 2025) | ✅ | None | Quarterly firewall review | Network Sec Lead | 2025-09-30
Req 2 | Apply secure configurations to all system components | Baseline config docs; CIS Benchmarks applied | ⚠️ | Not all configs benchmarked | Complete CIS hardening on all servers | SysAdmin Team | 2025-10-31
Req 3 | Protect stored account data | DB encryption at rest; tokenization | ✅ | None | Annual re-validation | DBA | 2025-12-31
Req 4 | Protect cardholder data with strong cryptography during transmission | TLS 1.2 enforced; Qualys scan reports | ✅ | None | Maintain TLS; monitor deprecations | Network Sec Lead | 2025-12-31
Req 5 | Protect all systems and networks from malicious software | EDR reports; AV signatures auto-updated | ✅ | None | Annual AV effectiveness test | IT Sec Ops | 2025-09-30
Req 6 | Develop and maintain secure systems and software | Patch mgmt logs; OWASP ZAP scans | ⚠️ | Patch cycles exceed 30 days for some servers | Accelerate patching; monthly cycle | Patch Mgmt Lead | 2025-10-15
Req 7 | Restrict access to system components and cardholder data by business need to know | Access matrix; least privilege documented | ✅ | None | Review access quarterly | IT Sec Ops | 2025-09-30
Req 8 | Identify users and authenticate access to system components | MFA logs; AD user list | ⚠️ | MFA not enforced for all admin accounts | Extend MFA to all privileged accounts | AD Admin | 2025-10-15
Req 9 | Restrict physical access to cardholder data | Server room access logs | ✅ | None | Annual physical access audit | Facilities Manager | 2025-12-31
Req 10 | Log and monitor all access to system components and cardholder data | Splunk SIEM logs; retention 12 months | ✅ | None | Ensure logs retained per PCI reqs | SOC Manager | 2025-09-30
Req 11 | Test security of systems and networks regularly | Quarterly external ASV scans | ⚠️ | Last internal penetration test >12 months | Schedule pentest Q3 2025 | AppSec Lead | 2025-11-30
Req 12 | Support information security with organizational policies and programs | InfoSec Policy v1.2; annual awareness training | ✅ | None | Annual review | CISO | 2025-12-31