## Risk Register
Risk ID | Asset/Process | Threat | Vulnerability | Impact (1-5) | Likelihood (1-5) | Existing Controls | Recommended Treatment | Owner | Target Date | Status | Risk Score | Inherent Risk
R1 | Customer Payment Data (Web App DB) | SQL Injection | Insufficient input validation / parameterization | 5 | 3 | Basic input validation; weekly vulnerability scans | Implement parameterized queries; WAF rules; quarterly pentest | AppSec Lead | 2025-11-30 | Open | 15 | High
R2 | Employee Laptops (Workstations) | Credential Theft / Phishing | Weak password policy; limited MFA coverage | 4 | 4 | EDR deployed; security awareness training quarterly | Enforce MFA; password manager rollout; phishing simulations | IT Operations Manager | 2025-10-15 | Open | 16 | High
R3 | Cloud Storage (S3/Blob) | Data Leakage / Misconfiguration | Public access not blocked by default; missing encryption-at-rest tag | 5 | 2 | Cloud Security Posture Management (CSPM) in place | Block public access at org level; enforce encryption policies | Cloud Platform Lead | 2025-09-30 | In Progress | 10 | Medium
R4 | Third-Party Payment Processor | Vendor Breach / Outage | Limited due diligence; no formal SLA review cadence | 4 | 3 | PCI DSS attestation from vendor; basic vendor review done in 2024 | Formalize vendor risk assessments; SLA review; incident comms plan | Vendor Risk Manager | 2025-12-15 | Open | 12 | High
R5 | Privacy / Data Subject Requests (DSAR) | Regulatory Non-Compliance (GDPR) | No formal DSAR workflow or tracking SLA | 4 | 3 | Privacy policy published; informal process via support | Implement DSAR workflow; define SLAs; train staff; evidence tracking | Data Protection Officer | 2025-10-31 | Open | 12 | High